## Project Info
Midas D5L6 De-Lidder — Project Tracker
Customer | Spectrum Control, Inc. | Sales Order | SO2524915
Customer PO | MX32667 | Equipment | Midas D5L6 De-Lidder
Primary Contact | Federico Rodarte | Backup Contact | Ivonne Castillo
Ship To | WTS Corporation Inc., 9540 Joe Rodriguez, El Paso, TX 79927
Target Ship Date | June 26, 2026 | Project Status | Active build
Last Update | 2026-05-19 | Revision | 2
Communication Cadence
Written status to Federico every Friday morning until ship. Cover: parts received that week, build/test progress, any schedule change the moment it is known.

## Procurement
Procurement Tracker
Item | Vendor | PO # | Order Date | Plan Receive | Actual Receive | Status | Notes
Beckhoff IPC + drives + touch panel | Beckhoff Automation | TBD | 2026-05 | 2026-05-22 | Confirmed wk of 5/18 | Confirmed arrival this week | Unlocks bench code dev
Applied Motion motor + drive | Applied Motion Products | TBD | 2026-05 | 2026-05-25 | Confirmed | Confirmed, to George by 5/25
Antistatic clear lid (D5LD-01) | Vendor identified | TBD | 2026-05-15 | 2026-06-12 |  | Ordered, 4 wk lead | Ships direct to AZ for final install (not blocking George)
Cutter motor (D5DC-01) | Groschopp | PO26021550 | 2026-02 | 2026-04-06 | 2026-04 | Received
Chicago Dial Indicators (D5HSVS11, D5LTBS10) | Chicago Dial Indicator | PO26121668 | 2026-04 | Before 6/1 |  | Confirmed ETA, arrives before 6/1
Viking machined + anodized parts | Viking Machine & Tool | PO26101639 | 2026-01 | 2026-04 | 2026-04 (qty 3 ea) | Received
Anodize / plate / coatings (55 items) | Coating Systems Inc. | TBD | 2026-05-19 | 2026-05-29 |  | Shipping to coater this week | 1 week coating turnaround
Turnpack in-house parts (9 items) | Turnpack, LLC | Internal | 2026-05-11 | 2026-05-22 |  | CAD released, fab in progress | D5ELPB10E, D5ELHR16, D5MSTL60 CAD complete
Carriage plate (D5LS0602) + grind | Turnpack in-house | Internal | 2026-05-11 | 2026-05-22 |  | Fab + grind in progress
Rework Tech components (24 items) | Rework Tech | Various | Various | On hand | On hand | Received per BOM
Digi-Key / Mouser electrical (75+) | Digi-Key / Mouser | Various | Various | On hand | On hand | Received per BOM
McMaster-Carr hardware (31 items) | McMaster-Carr | Various | Various | On hand | On hand | Received per BOM

## Milestones
Milestone Tracker — Plan vs. Actual
# | Milestone | Owner | Plan Date | Actual Date | Status / Notes
1 | CAD release for 3 in-house items | Chris/Brandon | 2026-05-13 | 2026-05-19 | ✓ COMPLETE
2 | Beckhoff hardware in-house at Turnpack (AZ) | Beckhoff | 2026-05-22 |  | Confirmed arrival this week
3 | Turnpack in-house fab complete (incl. carriage plate) | Turnpack shop | 2026-05-22 |  | Fab in progress
4 | Applied Motion motor received at George (MA) | Applied Motion | 2026-05-25 |  | Confirmed ship date
5 | Parts ship to Coating Systems Inc. | Turnpack shop | 2026-05-22 |  | Shipping this week
6 | Bench code dev start (PLC/HMI/recipes on bench) | Chris Berger | 2026-05-25 |  | See Bench Code Dev tab
7 | Coatings return + ship to George (MA) | Coating Systems Inc. | 2026-05-29
8 | Antistatic lid received at AZ (direct to Turnpack) | Lid vendor | 2026-06-12 |  | 4 wk lead, final install in AZ
9 | Full mechanical assembly start at George | George Bloom | 2026-06-01
10 | Full mechanical assembly complete (60 hr) | George Bloom | 2026-06-10
11 | Bench code dev complete + bench-tested | Chris Berger | 2026-06-12
12 | Crate + freight MA → AZ (5-day LTL) | Carrier | 2026-06-17
13 | On-machine integration + lid install + motion tuning | Chris Berger | 2026-06-23 |  | 1 week with bench code in place
14 | Factory Acceptance Test (FAT) | Chris Berger | 2026-06-25 |  | 2-day FAT
15 | Crate at Turnpack (AZ) + handoff to carrier | Turnpack shop | 2026-06-26
16 | ★ SHIP TO WTS BROKER (El Paso) | Carrier | 2026-06-26 |  | TARGET COMMITTED DATE — ZERO FLOAT

## Weekly Updates
Weekly Update Log — Friday Cadence to Federico
Friday Date | Parts Received This Week | Build / Test Progress | Schedule Changes | Risk / Next Week
2026-05-15 | (no parts due this week) | ✓ CAD released for 3 in-house items; Turnpack shop fab kickoff | Initial schedule baseline issued Mon 5/19 — target ship 6/26/2026 committed | ✓ Beckhoff arrival, ✓ Applied Motion confirmed, ✓ lid PO placed, ✓ CDI ETA confirmed
2026-05-22 | Beckhoff IPC + drives + panel (AZ); Applied Motion en route to George | Bench code dev W1 kickoff (TwinCAT project, EtherCAT scan, NC axis config); Turnpack in-house fab completing | On plan — 6/26 holds | Coatings shipping to vendor; carriage plate fab in progress
2026-05-29
2026-06-05
2026-06-12
2026-06-19
2026-06-26

## Bench Code Dev
Beckhoff Bench Code Development Plan
Three-week parallel development sprint while George builds mechanical in MA. Runs on bench Beckhoff hardware (in-house wk of 5/18). Goal: fully bench-tested PLC + HMI + recipe stack ready for 1-week on-machine integration when partial assembly arrives in AZ.
Sprint | Week | Workstream | Deliverable | Plan Complete | Status / Notes
W1 | 5/25-5/29 | Foundation | TwinCAT 3 project, EtherCAT scan, I/O map | 2026-05-26
W1 | 5/25-5/29 | Foundation | Applied Motion drives configured as NC axes | 2026-05-27 | Verify EtherCAT comms + encoder feedback
W1 | 5/25-5/29 | Foundation | Safety I/O architecture (E-stop, guards, light curtain) | 2026-05-28
W1 | 5/25-5/29 | Foundation | Base state machine skeleton (Init/Idle/Manual/Auto/Fault) | 2026-05-29
W2 | 6/1-6/5 | Motion | Homing routines for all axes | 2026-06-02
W2 | 6/1-6/5 | Motion | Jog + move-to-position blocks | 2026-06-03
W2 | 6/1-6/5 | Motion | Cutter cycle sequence (delid motion profile) | 2026-06-04
W2 | 6/1-6/5 | HMI | Run screen, Manual mode, Alarms, Diagnostics screens | 2026-06-05
W2 | 6/1-6/5 | HMI | Operator / Maintenance access levels | 2026-06-05
W3 | 6/8-6/12 | Recipes | Recipe file structure + load/save/edit logic | 2026-06-09 | Package type + cutter params
W3 | 6/8-6/12 | Recipes | Recipe execution integrated with motion blocks | 2026-06-10
W3 | 6/8-6/12 | Logging | Cycle counter + alarm history + event log | 2026-06-11
W3 | 6/8-6/12 | Verification | Full bench dry-run with drives spinning (no machine) | 2026-06-12 | Document any items needing real machine
W3 | 6/8-6/12 | Docs | Code documentation + operator quick-reference draft | 2026-06-12
On-machine | 6/17-6/23 | Integration | Mount Beckhoff to machine, power-up, I/O verify | 2026-06-18 | Day 1 after MA->AZ freight
On-machine | 6/17-6/23 | Tuning | Motion tuning (PID, accel/decel, jerk limits) | 2026-06-19
On-machine | 6/17-6/23 | Tuning | Safety verification with real I/O | 2026-06-22
On-machine | 6/17-6/23 | Tuning | Process test with sample packages, iterate | 2026-06-23 | Pre-FAT readiness check